## README
Advanced FETP implementation-pilot protocol workbook
Version1 ¦ 17 August 2026 ¦ Final coordinated manuscript, independent fidelity measurement, complete analysis and dissemination plans
Study | Implementing a competency-based Advanced Field Epidemiology Training Programme in Sierra Leone: protocol for a mixed-methods pilot evaluation | Protocol element | Count
Design | Prospective single-cohort longitudinal mixed-methods implementation pilot; curriculum quality and implementation readiness are evaluated as distinct questions; a conflict-screened Independent Research and Evaluation Team (IRET) controls research data, fidelity scoring, analysis and reporting. | Outcomes | 28
Planned cohort | 15 | Fidelity components | 20
Accredited field sites | 8 | Progression criteria | 8
Programme duration | 24 months, with at least 68 qualifying field-practice weeks | Instruments | 15
Evaluation period | Months -3 to 30 | Research milestones | 13
Core deliverables | Two authentic investigations; one led analytic investigation; thesis/dissertation; two internal/national articles; one peer-reviewed manuscript; policy brief; presentation | Implementation strategies | 12
Workbook purpose | Locked outcome definitions, schedules, component-level fidelity criteria and tools, independent-team roles, data locks, analysis specifications, reporting shells, dissemination outputs, continuity controls, resources and costing assumptions. | Field-site criteria | 12
Outcome hierarchy | Primary: O03 overall implementation fidelity at Month 24. Key secondary: O04 field-practice attainment, O05 retention, O06 acceptability, O07 appropriateness, O08 perceived feasibility and O09 primary-data completeness. Other outcomes remain secondary, exploratory, process, economic, equity, service or non-negotiable conditions. | Cost categories | 11
Fidelity scoring | Implementation fidelity is delivery, receipt and documentation of the intervention and implementation strategies as prespecified, while approved adaptations preserve core functions. The IRET independently scores 20 unweighted components from registered source evidence. Two reviewers verify every component; a third adjudicates unresolved differences. Partial, unknown and disputed status count as not met; not-due items are excluded; critical components remain non-compensatory. | Additional control sheets | 6
Use rule | Do not alter locked definitions after enrolment without a dated protocol amendment.
Missing data | Retain explicit missing/unknown categories; do not convert missing documentation into resident failure without verification.
Disclosure | Suppress cells smaller than five and review quotations/site labels for deductive disclosure.
Research separation | Research consent and voluntary responses remain separate from programme admission, assessment and employment. IRET members receive only approved programme-record extracts and hold no progression role.
AI restriction | Do not upload identifiable or confidential participant, patient, outbreak or institutional data to unapproved digital or automated systems.
Independent research team | IRET roles: research lead; fidelity/quantitative analyst; qualitative lead and interviewers; data manager; health economist. Members do not teach, mentor, supervise, assess, examine or vote on progression.
Analysis governance | IRET validates and locks datasets before analysis. Programme personnel may correct factual extraction errors during the defined query window but cannot select fidelity status, alter locked analyses or suppress results.
Dissemination | Quarterly dashboards, Month-12 interim report, Month-24 final implementation and scale-up report, Month-30 follow-up report, plain-language summaries, policy products, peer-reviewed articles, conference outputs and repository materials are prespecified.

## Outcomes
Code | Outcome | Operational definition | Source | Timing | Analysis role
O01 | Reach | Number enrolled divided by number eligible and offered a place; distribution by geography, profession, sector, gender and other approved equity variables. | Recruitment and enrolment register | Pre-launch/Month 0 | Secondary implementation outcome
O02 | Site adoption | Number of eligible sites accredited and active divided by number invited; reasons for non-adoption or withdrawal. | Site register and interviews | Pre-launch; Month 12; Month 24 | Secondary implementation outcome
O03 | Overall fidelity | Number of due and applicable components independently adjudicated as meeting their prespecified standard divided by due and applicable components at Month 24; all 20 components and every critical component are reported separately. | IRET Instrument I07 fidelity assessment and verification package linked to registered programme source records | Prelaunch readiness; quarterly; final Month-24 lock | Primary implementation outcome
O04 | Field-practice attainment | Proportion of residents completing at least 68 qualifying supervised field-practice weeks by Month 24 or approved completion window. | Verified field-week log | Monthly; Month 24 | Key secondary feasibility outcome
O05 | Retention | Proportion of enrolled residents active at Months 12 and 24; reasons and timing of interruption or withdrawal. | Cohort register | Continuous; Month 12; Month 24 | Key secondary feasibility outcome
O06 | Acceptability | Mean and distribution of the four-item AIM score among residents, mentors, supervisors and faculty. | AIM survey | Months 6, 12, 18 and 24 | Key secondary implementation outcome
O07 | Appropriateness | Mean and distribution of the four-item IAM score among residents, mentors, supervisors and faculty. | IAM survey | Months 6, 12, 18 and 24 | Key secondary implementation outcome
O08 | Perceived feasibility | Mean and distribution of the four-item FIM score among residents, mentors, supervisors and faculty. | FIM survey | Months 6, 12, 18 and 24 | Key secondary implementation outcome
O09 | Data completeness | Available required primary-data fields divided by expected required fields, by instrument and timepoint. | Data-quality dashboard | Quarterly | Key secondary study-process outcome
O10 | Instructional dose | Sessions and practical exercises delivered divided by planned; resident participation and low-bandwidth substitutions. | Session and exercise register | Monthly/quarterly | Fidelity component
O11 | Mentorship dose | Completed documented mentor contacts divided by planned monthly contacts; quarterly review completion and feedback timeliness. | Mentor log and portfolio system | Monthly/quarterly | Fidelity and secondary outcome
O12 | Progression review fidelity | Formal progression reviews completed on time with required evidence and documented decisions. | Progression records | Months 6, 12, 18 and 24 | Fidelity component
O13 | Portfolio completion | Proportion completing all eight field-product categories with every critical criterion at competent level or above. | Portfolio and rubric database | Months 18, 24 and completion window | Educational outcome
O14 | Field-product quality | Criterion and total scores on the common four-point rubrics; distribution by product, site and review point. | Assessor rubrics | Continuous; Months 12, 18 and 24 | Educational outcome
O15 | Outbreak evidence | Number of authentic investigations per resident; proportion completing two; proportion leading at least one analytic investigation; quality and timeliness. | FP2 evidence map and outbreak records | Continuous; Month 24 | Key educational/service outcome
O16 | Research milestone attainment | Proportion meeting each of 13 research, thesis/dissertation and publication milestones within the permitted window. | Milestone register | Months 5–24 | Key educational outcome
O17 | Thesis/dissertation completion | Proportion receiving independent approval after defence and corrections by Month 24 or approved completion window. | Examination and repository records | Months 23–24 | Key graduation outcome
O18 | Internal/national publications | Number and proportion producing two accepted or published articles through defined internal or national editorial channels from distinct field products. | Editorial and publication records | Months 12, 18, 24 and 30 | Key dissemination outcome
O19 | Peer-reviewed manuscript | Proportion with a lead-author manuscript independently certified and submitted; acceptance/publication status through Month 30. | Manuscript, submission and journal records | Months 22, 24 and 30 | Key dissemination outcome
O20 | Policy and scientific dissemination | Proportion completing a policy/decision brief and an oral or poster presentation; audience feedback. | Portfolio and event records | Months 18–24 | Dissemination outcome
O21 | Competency change | Change in scenario-based applied knowledge/reasoning score and calibrated workplace entrustment ratings from baseline. | Applied assessment and competency record | Months 0, 12 and 24 | Exploratory educational outcome
O22 | Assessor agreement | Weighted kappa for ordinal critical-criterion decisions and two-way random-effects absolute-agreement ICC for composite scores on double-rated products. | Paired assessor rubrics | Calibration and throughout | Exploratory assessment-quality outcome
O23 | Recommendation uptake | Resident recommendations accepted, initiated or completed within six months, divided by recommendations with a named decision owner and follow-up plan. | Management response and verification log | Continuous; Month 24 and 30 | Service outcome
O24 | Verified system contribution | Count and description of independently verified changes to surveillance, response, programmes, policy, data systems or workforce linked to resident work. | Document review and decision-maker interviews | Months 24 and 30 | Service contribution outcome
O25 | Implementation and programme cost | Total and component cost; cost per enrolled resident, retained resident, graduate, completed product, outbreak investigation, publication and thesis/dissertation. | Time and cost ledger | Monthly; Months 12, 24 and 30 | Economic outcome
O26 | Equity of exposure and outcomes | Descriptive differences in field opportunities, mentor contact, product completion, progression and completion across approved equity strata; small cells suppressed. | Linked programme and survey data | Quarterly; Month 24 | Cross-cutting equity outcome
O27 | Safety, safeguarding and integrity | Number, type, severity, response time and resolution of field-safety, privacy, coercion, retaliation, assessment-integrity or scientific-integrity events. | Incident and safeguarding log | Continuous | Non-negotiable condition, not a graded outcome
O28 | Sustainability readiness | Domestic financing, local faculty share, mentor retention, governance integration, field-site continuation, curriculum maintenance and graduate deployment readiness. | Sustainability scorecard and interviews | Months 18, 24 and 30 | Secondary implementation outcome

## Data_Schedule
Source | Population | Baseline/M0 | M6 | M12 | M18 | M22-23 | M24 | M30 | Outcomes
Recruitment/eligibility register | Programme applicants and residents | Pre-launch/Month 0 | [6 empty] | O01
Resident baseline profile and applied assessment | Residents | Month 0 |  | Month 12 |  |  | Month 24 |  | O01, O21, O26
Field-week, deployment and attendance logs | Residents/sites | Monthly | Monthly | Monthly | Monthly | Monthly | Monthly | Month 30 verification | O03, O04, O05, O10, O15
Mentor and supervisor contact logs | Residents/mentors/supervisors | Monthly | Monthly | Monthly | Monthly | Monthly | Monthly |  | O03, O11
AIM/IAM/FIM and experience survey | Residents, mentors, supervisors, faculty |  | Month 6 | Month 12 | Month 18 |  | Month 24 |  | O06–O08, O26
Field-product rubrics and portfolio evidence | Residents/assessors | Continuous | Month 6 | Month 12 | Month 18 | Continuous | Month 24 | Month 30 follow-up | O13–O20, O22
Research/thesis/publication milestones | Residents/supervisors | Month 5 onward | Month 6 | Month 12 | Month 18 | Month 22–23 | Month 24 | Month 30 | O16–O20
CFIR-informed interviews | Purposive stakeholders | Pre-launch | Month 6 | Month 12 | Month 18 |  | Month 24 | Month 30 | O02, O06–O08, O24, O28
Focus groups | Residents/mentors/supervisors |  |  | Month 12 |  |  | Month 24 |  | O06–O08, O11, O26
Independent fidelity assessment, source verification and adaptation audit | IRET using programme source records; programme staff respond only to factual queries | Pre-launch | Quarterly | Quarterly | Quarterly | Quarterly | Month 24 | Month 30 | O03, O10-O12, O27, O28
Cost and resource-use ledger | Programme/finance actors; IRET health economist | Pre-launch | Monthly | Monthly | Monthly | Monthly | Monthly | Month 30 close-out | O25
Management response/system contribution verification | Decision-makers/products |  |  | Continuous | Continuous | Continuous | Month 24 | Month 30 | O23, O24
Safety, safeguarding and integrity log | All stakeholder groups | Continuous | Continuous | Continuous | Continuous | Continuous | Continuous | Month 30 close-out | O27

## Fidelity
ID | Component | Fidelity dimension | Level/unit | Operational standard | Class | Numerator | Denominator | Primary evidence | Corroborating evidence | Frequency | IRET verification | Primary status rule
F01 | Governance active | Governance adherence and quality | Required governance bodies due | Steering, assessment, research/thesis and safeguarding/evaluation functions have approved terms of reference and meet at least quarterly. | Critical | Bodies meeting with complete terms, minutes and decisions | bodies due | Approved terms, signed minutes, attendance and decision log | Attendance register, quarterly decision log and overdue-action review | Quarterly; IRET extraction and two-reviewer verification | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F02 | Ethics and institutional authorization | Ethics adherence | Research authorization requirements | Written SLESRC approval or waiver, NPHA authorization and approved amendments precede research data collection. | Critical | Required approvals and amendments present before collection | requirements due | SLESRC/NPHA letters, amendment register, research start log | Research start log, amendment register and data-collection timestamps | Prelaunch and each amendment; two-source verification | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F03 | Financing and operational readiness | Readiness adherence | Programme level | Core programme and evaluation costs for the first 12 months are committed before cohort launch, with a documented continuity plan. | Critical | Eligible first-year resources committed and continuity plan present | required package | Signed budgets, commitment records, continuity plan and ledger | Cost ledger, continuity-plan review and financing exception log | Prelaunch; quarterly verification | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F04 | Field sites accredited | Reach and adherence | Eight field sites | All eight placement sites meet every critical criterion and at least 80% of scored readiness criteria before resident placement. | Critical | Sites passing all critical and at least 80% scored criteria | 8 sites | I06 checklists, source evidence and accreditation decisions | Source documents for critical criteria, site visit notes and corrective-action verification | Preplacement, M12 and M24 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F05 | Resident and host agreements | Reach and adherence | Residents and host institutions | Every resident and host institution completes protected-time, data-access, deployment, supervision and publication agreements. | Core | Complete agreements | 15 residents and all host institutions due | Signed agreement register and exception log | Exception log, placement register and host confirmation | Preplacement; M6 and M12 review | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F06 | Faculty and mentor preparation | Reach, dose and quality | Assigned programme actors | At least 90% of assigned faculty, mentors, supervisors and assessors complete required preparation before role assumption. | Core | Actors completing required preparation | actors assigned | Training register, attendance, knowledge check and calibration results | Knowledge check, calibration results and role-assumption date | Before role; refresh M6, M12 and M18 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F07 | Modules delivered | Content adherence and adaptation | 17 modules | All 17 modules receive the planned facilitated, practice and field-transfer components or approved fidelity-preserving adaptations. | Core | Modules with facilitated, practice and field-transfer elements or approved adaptation | 17 | Module plans, materials, registers, field-transfer evidence and I12 ID | Field-transfer evidence, resident experience data and linked I12 adaptation record | Quarterly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F08 | Sessions delivered | Dose and timeliness | 70 planned sessions due | At least 85% of 70 planned sessions are delivered within the permitted schedule. | Core | Sessions delivered within schedule | sessions due | Session register, agenda, attendance or platform extract | Attendance/platform extract, cancellation log and permitted-schedule record | Monthly; quarterly lock | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F09 | Exercises delivered | Dose and quality | 36 practical exercises due | At least 85% of 36 planned practical exercises are completed with feedback. | Core | Exercises completed with recorded feedback | exercises due | Exercise archive, feedback record and completion register | Feedback record, completion register and exercise archive | Monthly; quarterly lock | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F10 | Field-practice opportunity and supervision delivered | Adherence, dose and reach | Active resident-placement months | Every active resident receives an accredited placement, protected field time, qualifying assignments, named supervision and a verified field-week recording system throughout the planned period; gaps trigger documented programme corrective action. | Critical | Resident-placement months meeting all delivery conditions | Active resident-placement months due | Placement and workplan records, assignment letters, supervisor logs, field-week-system audit and corrective-action records | Deployment records, resident workload data and closed corrective-action verification | Monthly; quarterly lock; full Month-24 verification | Reviewer 1 extraction; independent Reviewer 2 verification of every component; third adjudicator for unresolved disagreement | Met only when the full operational threshold is reached. Partial, unknown and unresolved disputed status count as not met; not-due excluded; not-applicable requires written IRET adjudication.
F11 | Named mentorship and supervision | Reach and continuity | Active residents | Every active resident has a named technical mentor and workplace supervisor throughout placement. | Critical | Residents with named mentor and workplace supervisor throughout period | active residents | Assignment letters, change register and contact logs | Mentor/supervisor change register and contact log | Monthly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F12 | Mentor contacts | Dose and quality | Planned mentor contacts and reviews | At least 80% of planned monthly mentor contacts and quarterly formal reviews are documented. | Core | Completed documented contacts and reviews | contacts and reviews due | Mentor log, feedback record and quarterly review form | Feedback record, formal-review form and timeliness log | Monthly; quarterly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F13 | Progression reviews | Timeliness and quality | Formal reviews due | At least 90% of due progression reviews occur within four weeks of the planned month and record evidence, decision and actions. | Core | Reviews within four weeks with evidence, decision and actions | reviews due | Progression forms, evidence checklist and minutes | Progression minutes, action register and remediation record | M6, M12, M18 and M24 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F14 | Portfolio assessment | Assessment adherence and quality | Products due for assessment | Every resident receives rubric-based assessment for all products due by each progression point; critical failures trigger remediation. | Critical | Due products receiving rubric assessment and remediation when required | products due | Portfolio platform, signed rubrics, ownership evidence and remediation log | Resident-ownership statement, oral-defence record and progression minutes | Quarterly; progression points | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F15 | Outbreak opportunity and evidence | Reach and content adherence | 15 residents | Every resident receives two authentic investigation opportunities or a documented programme-led corrective placement; at least one investigation permits resident analytic leadership. | Critical | Residents with two authentic opportunities and one analytic leadership role | enrolled cohort | Deployment orders, role statements, protocols, analyses, reports and after-action records | Outbreak trigger record, stakeholder verification and after-action review | Continuous; M24 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Official primary source required; self-report alone cannot establish this critical component. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F16 | Research governance by Month 12 | Reach and timeliness | Active residents at M12 | At least 80% of active residents receive protocol-defence approval and ethics/data-governance authorization by Month 12 or an approved recovery deadline. | Core | Residents with protocol defence and ethics/data-governance authorization or approved recovery date | active residents | I09 milestone form, committee decision and authorization letter | Committee decision, approval/waiver letter and approved recovery plan | Month 12 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F17 | Year-2 research protection | Dose and quality | Active residents during M13-23 | Residents receive planned protected time and access for implementation, analysis and writing during Months 13–23. | Core | Residents receiving protected time and required access | active residents | Approved workplans, workload survey, supervisor log and access record | Resident workload survey, supervisor record and access exception log | Monthly; quarterly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F18 | Publication pathway | Reach and quality | Active residents | Each resident receives publication mentorship, approved internal channels, journal-legitimacy screening and editorial tracking. | Core | Residents receiving publication mentor, internal channel, journal screen and editorial tracking | active residents | Mentor assignment, editorial log, journal screen and correspondence | Editorial correspondence, output tracker and resident experience data | Quarterly; M24 | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F19 | Assessment calibration | Quality assurance | High-stakes assessors and products | All high-stakes assessors complete calibration; every thesis/dissertation and at least 25% of other products receive independent double rating. | Core | Calibrated assessors / assigned assessors; independently double-rated products | products required | Preparation register, calibration results and paired rubrics | Paired rubrics, disagreement review and calibration refresh record | Before role; quarterly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
F20 | Adaptation, cost and quality tracking | Adherence and quality control | Quarterly control cycles due | Quarterly adaptation logs, cost ledgers, data-quality audits and programme feedback cycles are complete. | Core | Complete adaptation, cost, data-quality, fidelity-lock and feedback cycles | cycles due | I12 log, cost ledger, data-quality dashboard, signed I07 lock and action log | Programme response, closed-action record and quarterly control-cycle register | Quarterly | Reviewer 1 extraction; independent Reviewer 2 verification; third adjudicator for unresolved differences. Registered primary source plus corroboration when available. | Met only when the full operational threshold is reached. Partial, unknown and disputed status count as not met; not-due is excluded; not-applicable requires written IRET approval.
Definition | Implementation fidelity is the extent to which the intervention and its implementation strategies are delivered, received and documented as prespecified while approved adaptations preserve core functions.
Overall score | 100 x components due and applicable that the IRET adjudicates as met / components due and applicable. The Month-24 score is primary; every component and all critical components are reported separately.
Status categories | Met; Partial; Not met; Unknown; Not due; Not applicable; Disputed. Partial, unknown and disputed count as not met in the primary analysis.
Critical rule | Critical components are non-compensatory and cannot be offset by the aggregate score. A critical component requires an official primary source and, when available, corroboration.
Data lock | The IRET lead signs each quarterly and Month-24 dataset. Later corrections create a new version and retain the previous value, reason, approver and date.

## Progression
Criterion | Green | Amber | Red | Basis for threshold
Overall implementation fidelity | At least 80% of due and applicable components independently adjudicated as met and all critical components met | 60-79% or one remediable critical component missed | Below 60% or unresolved failure of a critical component | The IRET applies the prespecified component matrix and status rules. Eighty percent requires delivery of most due components. Every critical component must pass, so strengths cannot compensate for an ethical, safety or core-delivery failure.
Resident retention at Month 24 | ≥80% | 60–79% | <60% | Eighty percent represents 12 of 15 residents and requires retention of most of the complete first cohort while allowing a limited, recoverable interruption.
Field-practice attainment | ≥80% complete ≥68 weeks | 60–79% complete ≥68 weeks | <60% complete ≥68 weeks | The 68-week minimum follows Advanced FETP accreditation. Eighty percent represents 12 of 15 residents and distinguishes a limited interruption from widespread failure.
Portfolio and graduation requirements | ≥80% complete all critical requirements within three months of scheduled end | 60–79% or delays judged recoverable | <60% or widespread non-recoverable gaps | Eighty percent requires most residents to complete every critical graduation requirement within the approved completion window; amber identifies recoverable delays.
Mentorship dose | ≥80% of planned contacts completed | 60–79% | <60% | Eighty percent requires delivery of most prespecified monthly contacts and quarterly reviews while allowing limited documented disruption.
Acceptability, appropriateness and feasibility | Each stakeholder group mean ≥4.0/5 and no major unaddressed qualitative concern | Mean 3.0–3.9 or remediable concerns | Mean <3.0 or persistent major concern | A mean of 4/5 indicates affirmative agreement rather than neutrality. Qualitative concerns remain decisive when an average conceals burden, inequity or harm.
Primary-data completeness | ≥90% | 75–89% | <75% | Ninety percent supports dependable progression and scale-up decisions while allowing limited operational missingness. Missing documentation is not coded as resident failure without verification.
Safety, safeguarding and integrity | No unresolved serious event; corrective systems function | Serious event resolved with verified corrective action | Unresolved serious event, coercion, retaliation, material privacy breach or assessment/scientific-integrity failure | Safety, safeguarding and integrity are non-compensatory. Any unresolved serious event or material integrity failure blocks scale-up regardless of aggregate performance.

## Instruments
ID | Instrument | Respondent/source | Content | Timing
I01 | Eligibility and enrolment form | Applicants/residents | Baseline demographics, professional background, geography, prior skills, access and equity variables | Month 0
I02 | Applied knowledge and reasoning assessment | Residents | Blueprint based on 102 terminal outcomes; two equivalent scenario forms; expert content review, cognitive testing and pilot administration with non-cohort users; keyed analytic rubric; authentic workplace evidence remains decisive. | Months 0, 12, 24
I03 | AIM/IAM/FIM survey | Residents, mentors, supervisors, faculty | Validated four-item acceptability, appropriateness and feasibility measures; 1–5 agreement response | Months 6, 12, 18, 24
I04 | Resident experience, workload and support survey | Residents | Protected time, field opportunity, mentorship, access, wellbeing, safety, equity and remediation experience | Months 6, 12, 18, 24
I05 | Mentor/supervisor delivery survey | Mentors and supervisors | Caseload, contact dose, feedback timeliness, support, barriers, opportunity and programme fit | Quarterly
I06 | Field-site readiness/accreditation checklist | Sites and programme quality team | Twelve criteria with critical pass/fail and scored domains | Pre-launch, Month 12, Month 24
I07 | Fidelity assessment and verification package | Independent Research and Evaluation Team using registered programme source records | Twenty-component assessment form; source-evidence register; independent second-review form; discrepancy/adjudication log; programme factual-query record; signed quarterly data lock and dashboard | Prelaunch readiness; quarterly; final Month-24 lock; Month-30 follow-up verification
I08 | Field-product rubric set | Residents/assessors | Common and product-specific four-point criteria, critical fail rules and resident ownership | Throughout
I09 | Research/thesis/publication milestone form | Residents/supervisors/committee | Thirteen milestones, evidence, decision, delay reason and recovery plan | Months 5–24
I10 | CFIR interview guide | Residents, mentors, supervisors, faculty, managers and decision users | CFIR determinants, mechanisms, adaptations, benefits, harms, equity, sustainability and scale-up; interviewer preparation, independence from assessment, reflexive field notes, longitudinal reinterviews and explicit information-power decisions. | Pre-launch, Months 6, 12, 18, 24, 30
I11 | Focus-group guide | Residents, mentors and supervisors | Shared experience of delivery, field opportunity, workload, learning, support and improvement | Months 12 and 24
I12 | Adaptation log | Programme adaptation focal point; IRET verifier | FRAME/FRAME-IS fields completed by programme staff and independently verified against core-function and fidelity records | At change; quarterly review
I13 | Safety, safeguarding and integrity event form | All stakeholders | Type, severity, immediate protection, notification, investigation, corrective action and closure | Continuous
I14 | Recommendation and system-contribution verification form | Decision-makers; IRET verification team | Recommendation owner, decision, implementation status, evidence and contribution narrative | Continuous; Months 24 and 30
I15 | Time and cost log | Programme/finance actors; IRET health economist | Actor, activity, duration, resource, quantity, unit cost, payer and cost classification | Monthly

## Research_Milestones
Code | Target | Milestone | Minimum evidence
R1 | Month 5 | Priority problem and concept note | Question, public health value, feasibility, initial design and named institutional user.
R2 | Month 6 | Supervision and field agreement | Research supervisor, field mentor, access plan, protected time, conflict and initial authorship discussion.
R3 | Month 8 | Evidence synthesis and framework | Reproducible search record, critical synthesis, gap statement and conceptual or causal framework.
R4 | Month 10 | Full protocol and statistical analysis plan | Objectives, design, variables, sampling, bias control, analysis, dissemination, timeline and budget.
R5 | Month 12 | Ethics and data-governance authorization | Written approval, waiver or classification; data-access, security, sharing, retention and incident plan.
R6 | Month 12 | Protocol defence | Multidisciplinary panel approval before field implementation.
R7 | Month 15 | Implementation and data-quality review | Progress, deviations, quality indicators, safety, corrective action and continued feasibility.
R8 | Month 18 | Reproducible primary analysis review | Locked dictionary, code, planned analyses, diagnostics, sensitivity work and interpretation log.
R9 | Month 19 | Results and interpretation seminar | Findings, limitations, equity, stakeholder interpretation and decision implications.
R10 | Month 21 | Complete thesis/dissertation draft | Full monograph, publication-based dissertation or integrated field-epidemiology thesis.
R11 | Month 22 | Peer-reviewed manuscript and policy package | Lead-author manuscript, reporting checklist, journal screen, policy brief and submission plan.
R12 | Month 23 | Independent examination and oral defence | Examiner reports, defence decision and corrections list.
R13 | Month 24 | Final approval, repository and publication handover | Corrections completed, final deposit, authorship confirmation and post-graduation editorial follow-up.

## Intervention
Component | Specification | Accountability | Timing | Fidelity evidence
Programme duration and field intensity | Twenty-four months; no less than 21 months and 68 weeks of qualifying supervised field practice; target approximately 75% field service. | Programme director; field-site supervisors | Month 0–24 | Calendar, placement records and field-week log
Competency-based instruction | Seventeen modules, 102 terminal outcomes, 70 facilitated three-hour sessions, 36 practical exercises and low-bandwidth alternatives. | Core and specialist faculty | Month 1–22 | Session register, learning-platform record and exercise archive
Mentorship and workplace supervision | Named technical mentor and workplace supervisor; mentor caseload normally no more than four residents; monthly technical contact and quarterly documented review. | Mentors; workplace supervisors; programme faculty | Month 0–24 | Learning agreement, contact log and feedback record
Authentic portfolio assessment | Eight field-product categories, common four-point rubrics, direct observation, documented resident ownership, oral defence and non-compensatory critical criteria. | Calibrated assessors; assessment committee | Month 1–24 | Portfolio system, rubric decisions and progression minutes
Outbreak investigation deliverable | Two distinct authentic outbreak or urgent field investigations per resident; resident leads at least one analytic investigation through response action and after-action learning. | Resident; outbreak lead; mentor; assessor | Opportunity-dependent, Month 3–23 | Role statement, protocols, analyses, reports, communication products and after-action review
Research and thesis/dissertation | Concept and supervision in year 1; approved protocol and governance route by Month 12; implementation, analysis, writing, examination and defence occupy most of year 2. | Resident; research supervisor; thesis committee | Month 5–24 | Milestone register, protocol, data/code, thesis/dissertation, examination and corrections
Publication and dissemination | Two accepted or published internal or national-channel articles from distinct field products; one lead-author peer-reviewed manuscript; one policy brief; one scientific presentation. | Resident; publication mentor; editorial focal point | Month 8–24; follow-up to Month 30 | Editorial correspondence, retrievable outputs, submission record and presentation evidence
Progression, remediation and graduation | Formal reviews at Months 6, 12, 18 and 24; documented recovery plans; final panel decision based on complete evidence, integrity and resident ownership. | Progression and graduation committee | Months 6, 12, 18 and 24 | Review forms, remediation plans, appeal record and final decision

## Strategies
ID | Strategy | Actor | Action | Dose/timing | Evidence
IS01 | Assess readiness and barriers | Programme implementation team | Governance, finance, faculty, field sites, data access, safety, digital access and resident support | Pre-launch Months −3 to 0; repeat Month 12 | Completed readiness matrix and action plan
IS02 | Establish governance and coalitions | NPHA and programme director | National steering, assessment, research/thesis, independent research/evaluation and safeguarding structures, plus resident representation | Pre-launch; quarterly | Terms of reference, attendance and decision log
IS03 | Accredit and prepare field sites | Programme faculty and quality team | Eight field sites assessed against critical and scored eligibility criteria; gaps corrected before placement | Pre-launch; annual renewal | Site accreditation decision and corrective-action record
IS04 | Prepare mentors, supervisors, faculty and assessors | Programme faculty leads | Role-specific training, calibration cases, feedback skills, learner support, ethics, equity and escalation procedures | Before cohort; refresh Months 6, 12 and 18 | Completion register and calibration results
IS05 | Create protected-time and access agreements | Programme director and host institutions | Resident field time, data permissions, outbreak deployment, research access, publication rights and supervisor responsibilities | Before enrolment; reviewed Month 6 and 12 | Signed agreements and exception log
IS06 | Provide central technical assistance | Programme hub and specialist network | Epidemiology, statistics, GIS, informatics, laboratory/genomics, One Health, ethics, communication, economics and writing consultation | Throughout; request-based and scheduled | Consultation log and response time
IS07 | Use blended and low-bandwidth delivery | Faculty and digital-learning coordinator | In-person blocks, synchronous virtual sessions, self-paced preparation, ECHO case discussions, printed/offline packs and deferred secure upload | Throughout | Dose delivered, connection failures and alternative used
IS08 | Audit and provide feedback | Independent Research and Evaluation Team | Extract and independently verify fidelity evidence; lock quarterly datasets; issue dashboards covering fidelity, field exposure, mentorship, products, research, publication, equity, cost and risks | Quarterly | I07 fidelity package, signed data lock, dashboard, programme factual response and closed-action record
IS09 | Facilitate remediation and learner support | Programme director, mentors and safeguarding focal point | Early identification, written recovery plan, additional coaching, reassessment, wellbeing support and appeal route | Triggered; reviewed monthly until closure | Remediation record and outcome
IS10 | Track and govern adaptations | Programme adaptation focal point; IRET verifier | Programme records each change; IRET verifies timing, rationale, level, core-function preservation and observed consequence | At each change; quarterly synthesis | FRAME/FRAME-IS adaptation log
IS11 | Track resources and costs | Finance officer and IRET health economist | Time-driven activity-based costing of implementation strategies and programme delivery; research-only costs separated | Monthly; quarterly reconciliation | Resource-use log and cost ledger
IS12 | Plan sustainability and scale-up | Steering committee and NPHA leadership | Domestic financing, local faculty, mentor pipeline, institutional placement, curriculum maintenance, data systems and graduate deployment | From Month 12; formal Month 24 and 30 | Sustainability plan and scale-up decision

## Field_Sites
Criterion | Minimum evidence | Classification
Institutional mandate | Site performs surveillance, response, programme, laboratory, data or One Health functions relevant to Advanced field epidemiology. | Critical
Field opportunities | Site can provide routine surveillance work and access to authentic investigations, evaluations or rotations. | Critical
Named supervision | A qualified workplace supervisor accepts written responsibilities and protected contact time. | Critical
Data access and governance | Site can authorize resident access to appropriate data under approved privacy, security and sharing arrangements. | Critical
Decision-maker access | Residents can present findings and obtain documented management response or follow-up. | Critical
Safety and safeguarding | Risk assessment, field safety, incident reporting, non-retaliation and wellbeing procedures operate. | Critical
Research feasibility | Site supports research/thesis access, permissions and protected implementation time. | Scored
Laboratory and specialist linkage | Site can connect residents to necessary laboratory, GIS, informatics, One Health or other specialists. | Scored
Digital and physical infrastructure | Secure computing, data storage, connectivity or workable offline alternatives exist. | Scored
Equitable opportunity | Site allocates outbreak, leadership, publication and research opportunities transparently. | Critical
Operational support | Travel, communication, printing, specimen or field resources can be mobilized when required. | Scored
Quality participation | Site accepts monitoring, feedback, adaptation logging and accreditation renewal. | Critical

## Costs
Category | Examples | Class | Method
Personnel – programme | Director, coordinator, faculty, mentors, supervisors, assessors, administration and finance | Programme delivery | Time logs × loaded hourly rate; donated labour valued at opportunity cost; common overhead allocated by recorded staff time or documented use
Personnel – evaluation | Investigators, data management, interviews, transcription, analysis and reporting | Research only | Time logs × loaded hourly rate; reported separately from routine programme delivery and scale-up cost
Resident support | Salary/stipend where applicable, protected time, travel, accommodation, communications and field allowances | Programme delivery | Financial ledger and host contribution
Training delivery | Venue, materials, learning platform, ECHO, printing, facilitation and low-bandwidth alternatives | Programme delivery/implementation strategy | Invoice and activity log
Field investigation | Transport, communications, PPE, specimen shipment, laboratory tests and emergency logistics | Programme/service | Event-specific microcosting
Digital infrastructure | Devices, software, servers, connectivity, power backup, maintenance and security | Capital/recurrent | Purchase price; straight-line annualization; three-year computer and five-year other durable-item base lives; 3% annual discount where timing exceeds one year; allocation by documented use
Research/thesis | Ethics, data collection, laboratory/field costs, supervision, examination, repository and corrections | Programme/academic | Milestone-specific ledger
Publication and dissemination | Internal editorial production, journal charges where approved, conference, policy brief and stakeholder meeting | Programme/academic | Output-specific ledger
Safeguarding and learner support | Safety training, incident response, wellbeing referral, accessibility and reasonable accommodation | Programme | Case/activity ledger
Governance and quality | Committee meetings, site accreditation, calibration, audit, feedback and adaptation tracking | Implementation strategy | Activity-based ledger
Contingency | Approved unplanned costs needed to protect core functions | Programme | Authorization and ledger

## Resources
Resource area | Minimum requirement
Governance | Programme steering committee; assessment committee; research/thesis committee; Independent Research and Evaluation Team; independent safeguarding function; resident representation; documented conflicts, appeals and version control.
Core staffing for 15 residents | Programme director (approximately 0.5 full-time equivalent), programme coordinator (1.0), monitoring/data officer (0.5), research/thesis coordinator (0.4), publication/editorial support (0.2), digital-learning support (0.3), and combined core epidemiology faculty capacity of at least 1.5 full-time equivalents. Final staffing follows workload analysis.
Mentorship and supervision | At least four prepared technical mentors for a usual maximum caseload of four residents, plus contingency cover; one accountable workplace supervisor at each of eight sites; access to substitute mentors and escalation support.
Specialist access | Biostatistics, GIS, informatics, laboratory/genomics, One Health/environment, emergency management, implementation/evaluation, economics, ethics, communication and qualitative research.
Assessment | At least six calibrated assessors; two independent examiners for each thesis/dissertation; secure portfolio platform; rubrics, calibration cases, appeals and double-rating plan.
Digital and analytic infrastructure | Secure laptops, encrypted storage, power backup, internet and offline alternatives; R or another auditable analytic environment; QGIS or equivalent; secure survey/database platform; learning and ECHO platform.
Field and laboratory operations | Travel, accommodation, communications, personal protective equipment, specimen and laboratory pathways, printing, field allowances under national policy and emergency-deployment arrangements.
Research and publication | Library and literature access, ethics and data-governance support, transcription/translation where approved, thesis examination, internal editorial channels, legitimate-journal screening and publication/dissemination resources.
Learner protection | Orientation, reasonable accommodation, wellbeing referral, confidential reporting, non-retaliation, workload monitoring, remediation, grievance and appeal procedures.
Independent research and evaluation | A conflict-screened research lead, fidelity/quantitative analyst, qualitative lead and interviewers, data manager and health economist. No member teaches, mentors, supervises, assesses, examines or votes on progression. The team controls consent, research collection, fidelity scoring, source verification, data locks, analysis and reporting.
Research systems and costing | Secure survey and fidelity database, source-evidence register, two-reviewer verification and adjudication logs, data-quality audits, qualitative capacity, transcription, version-controlled analysis, cost tracking and dissemination resources.
Financial continuity | Committed first-year core programme and independent evaluation resources before launch; second-year financing plan; contingency reserve; separation of programme delivery from research-only costs; domestic financing and sustainability plan.

## Core_Variables
Variable | Label | Type | Allowed values/range | Timing | Source | Outcome | Missing rule | Sensitivity
study_id | Unique coded participant/record identifier | text | Assigned code; no meaningful initials | All | All research sources |  | Required | Confidential
resident_id | Unique coded resident identifier | text | R001-R015 | All | Programme/evaluation linkage | O01-O28 | Required | Confidential
site_id | Coded field-site identifier | text | S01-S08 | All | Programme records | O02-O28 | Required | Sensitive
actor_role | Participant role | categorical | resident; mentor; supervisor; faculty; assessor; manager; decision user | All | All instruments |  | Required | Sensitive
wave | Measurement wave | categorical | prelaunch; M0; M6; M12; M18; M22-23; M24; M30; continuous | All | All instruments |  | Required | Non-sensitive
record_date | Date of source event or collection | date | YYYY-MM-DD | All | All instruments |  | Required | Sensitive
consent_survey | Consent for survey participation | boolean | yes; no; withdrawn | M0/role entry | Consent store |  | Required | Highly confidential
consent_interview | Consent for interview/focus group | boolean | yes; no; withdrawn | At invitation | Consent store |  | Required | Highly confidential
consent_record_linkage | Consent/approved route for programme record linkage | categorical | consent; waiver; no research use | M0/role entry | Consent store |  | Required | Highly confidential
profession | Professional discipline | categorical | Nationally approved categories | M0 | I01 | O01,O26 | Unknown allowed | Sensitive
sector | Employment sector | categorical | human health; animal health; environment; laboratory; data; other | M0 | I01 | O01,O26 | Unknown allowed | Sensitive
geography_group | Approved geographic stratum | categorical | region/district grouping | M0 | I01 | O01,O26 | Unknown allowed | Sensitive
gender_group | Ethics-approved gender category | categorical | approved categories | M0 | I01 | O01,O26 | Prefer not to say | Sensitive
accommodation_need | Reasonable accommodation requested | categorical | none; physical; sensory; digital; language; other | M0 | I01 | O26,O27 | Prefer not to say | Highly confidential
baseline_score | Applied knowledge/reasoning total score | number | 0-100 | M0 | I02 | O21 | Missing if absent | Sensitive
m12_score | Applied knowledge/reasoning total score | number | 0-100 | M12 | I02 | O21 | Missing if absent | Sensitive
m24_score | Applied knowledge/reasoning total score | number | 0-100 | M24 | I02 | O21 | Missing if absent | Sensitive
enrolment_status | Programme status | categorical | offered; enrolled; active; interrupted; withdrawn; completed | Continuous | Cohort register | O01,O05 | Required | Sensitive
withdrawal_date | Date of permanent withdrawal | date | YYYY-MM-DD | Continuous | Cohort register | O05 | Blank if not withdrawn | Sensitive
withdrawal_reason | Reason for interruption/withdrawal | categorical/text | approved categories + narrative | Continuous | Cohort register | O05,O26 | Blank if not applicable | Highly confidential
field_week_count | Verified qualifying field-practice weeks | number | 0-104 | Monthly | Field-week log | O03,O04 | Required | Sensitive
session_planned | Planned facilitated sessions | integer | 0-70 | Quarterly | Session register | O03,O10 | Required | Non-sensitive
session_delivered | Facilitated sessions delivered | integer | 0-70 | Quarterly | Session register | O03,O10 | Required | Non-sensitive
exercise_planned | Planned practical exercises | integer | 0-36 | Quarterly | Exercise register | O03,O10 | Required | Non-sensitive
exercise_completed | Practical exercises completed with feedback | integer | 0-36 | Quarterly | Exercise register | O03,O10 | Required | Sensitive
mentor_contacts_planned | Planned mentor contacts | integer | 0-30 | Quarterly | Mentor log | O03,O11 | Required | Sensitive
mentor_contacts_completed | Completed documented mentor contacts | integer | 0-30 | Quarterly | Mentor log | O03,O11 | Required | Sensitive
feedback_turnaround_days | Days from submission to substantive feedback | number | 0+ | Quarterly | Portfolio/mentor log | O11 | Missing if not applicable | Sensitive
progression_review_due | Scheduled progression review | categorical | M6; M12; M18; M24 | Review wave | Progression record | O12 | Required | Sensitive
progression_review_date | Actual review date | date | YYYY-MM-DD | M6/M12/M18/M24 | Progression record | O12 | Missing until review | Sensitive
progression_decision | Progression decision | categorical | progress; progress with actions; remediation; interruption; exit; graduate | M6/M12/M18/M24 | Progression record | O12,O13,O26 | Missing until decision | Highly confidential
product_code | Field-product category | categorical | FP1-FP8 | Continuous | Portfolio | O13,O14 | Required | Sensitive
product_status | Field-product status | categorical | not due; in progress; submitted; revision; pass; critical fail | Continuous | Portfolio | O13,O14 | Required | Sensitive
product_total_score | Composite product rubric score | number | 1-4 or derived average | Continuous | I08 | O14,O22 | Missing until rated | Sensitive
product_critical_pass | All critical product criteria competent | boolean | yes; no | Continuous | I08 | O13,O14 | Missing until rated | Sensitive
assessor_id | Coded assessor identifier | text | A001+ | Continuous | I08 | O22 | Required for rated product | Confidential
outbreak_id | Coded authentic investigation identifier | text | OB001+ | Continuous | Outbreak record | O15 | Missing if none | Sensitive
outbreak_authentic | Authentic qualifying investigation | boolean | yes; no | Continuous | FP2 evidence | O15 | Required | Sensitive
outbreak_resident_role | Resident role | categorical | participant; analyst; team lead; analytic lead; response lead | Continuous | FP2 evidence | O15,O26 | Required | Sensitive
outbreak_timeliness_days | Days from trigger to preliminary actionable output | number | 0+ | Continuous | Outbreak record | O15 | Missing if not calculable | Sensitive
outbreak_quality_score | FP2 rubric composite | number | 1-4 | Continuous | I08 | O15 | Missing until rated | Sensitive
research_milestone_code | Research milestone | categorical | R1-R13 | M5-M24 | I09 | O16 | Required | Sensitive
research_milestone_status | Milestone status | categorical | not due; on time; delayed; complete; waived by approved route | M5-M24 | I09 | O16 | Required | Sensitive
research_milestone_date | Actual milestone completion date | date | YYYY-MM-DD | M5-M24 | I09 | O16 | Missing until complete | Sensitive
thesis_status | Thesis/dissertation status | categorical | not due; draft; submitted; revisions; approved; not approved | M21-M24 | I09/examination | O17 | Required | Highly confidential
thesis_defence_date | Oral defence date | date | YYYY-MM-DD | M23 | Examination record | O17 | Missing until held | Sensitive
internal_publication_count | Accepted/published internal or national articles from distinct products | integer | 0-2+ | M12-M30 | Editorial records | O18 | Required | Sensitive
peer_manuscript_status | Lead-author peer-reviewed manuscript status | categorical | not started; draft; certified; submitted; revise; accepted; published; rejected/resubmit | M22-M30 | Editorial records | O19 | Required | Sensitive
peer_submission_date | Date of first legitimate-journal submission | date | YYYY-MM-DD | M22-M30 | Journal record | O19 | Missing until submitted | Sensitive
policy_brief_complete | Policy/decision brief complete | boolean | yes; no | M18-M24 | Portfolio | O20 | Required | Sensitive
scientific_presentation_complete | Oral/poster presentation complete | boolean | yes; no | M18-M24 | Portfolio/event record | O20 | Required | Sensitive
aim_score | Acceptability of Intervention Measure mean | number | 1-5 | M6/M12/M18/M24 | I03 | O06 | Missing if <3 items | Confidential
iam_score | Intervention Appropriateness Measure mean | number | 1-5 | M6/M12/M18/M24 | I03 | O07 | Missing if <3 items | Confidential
fim_score | Feasibility of Intervention Measure mean | number | 1-5 | M6/M12/M18/M24 | I03 | O08 | Missing if <3 items | Confidential
recommendation_id | Coded recommendation identifier | text | REC001+ | Continuous | I14 | O23,O24 | Required | Sensitive
recommendation_status | Implementation status | categorical | not started; planned; initiated; partial; complete; rejected; discontinued | Continuous/M30 | I14 | O23 | Required | Sensitive
system_contribution_verified | Independent system contribution verified | boolean | yes; no; uncertain | M24/M30 | I14 | O24 | Required | Sensitive
contribution_type | Type of verified change | categorical | surveillance; response; programme; policy; data system; workforce; other | M24/M30 | I14 | O24 | Missing if none | Sensitive
cost_category | Cost category | categorical | From Costs sheet | Monthly | I15 | O25 | Required | Financial
resource_quantity | Resource quantity | number | 0+ | Monthly | I15 | O25 | Required | Financial
unit_cost_local | Unit cost in local currency | number | 0+ | Monthly | I15 | O25 | Required | Financial
cost_total_local | Derived total cost | number | quantity x unit cost | Monthly | I15 | O25 | Derived | Financial
equity_exposure_flag | Unequal opportunity or support concern | boolean | yes; no; under review | Quarterly | Programme/survey | O26 | Required | Highly confidential
event_id | Safety/safeguarding/integrity event code | text | EV001+ | Continuous | I13 | O27 | Missing if none | Highly confidential
event_type | Event classification | categorical | field safety; privacy; coercion; retaliation; assessment; scientific integrity; wellbeing; other | Continuous | I13 | O27 | Required for event | Highly confidential
event_severity | Event severity | categorical | near miss; minor; moderate; serious; life-threatening/material breach | Continuous | I13 | O27 | Required for event | Highly confidential
event_resolved | Event resolution status | categorical | open; contained; corrective action; resolved; external review | Continuous | I13 | O27 | Required for event | Highly confidential
sustainability_score | Composite sustainability readiness score | number | Protocol-defined 0-100 or domain profile | M18/M24/M30 | Scorecard | O28 | Required | Sensitive
fidelity_component_id | Fidelity component | categorical | F01-F20 | Quarterly | I07 | O03 | Required | Sensitive
fidelity_standard_met | Component standard met | boolean | yes; no; not applicable | Quarterly | I07 | O03 | Required | Sensitive
adaptation_id | Adaptation record code | text | AD001+ | At change | I12 | O03,O28 | Missing if none | Sensitive
adaptation_core_preserved | Core function preserved | categorical | yes; no; uncertain | At change | I12 | O03,O28 | Required for adaptation | Sensitive
required_fields_expected | Required fields expected | integer | 0+ | Quarterly | Data-quality dashboard | O09 | Required | Non-sensitive
required_fields_available | Required fields available | integer | 0+ | Quarterly | Data-quality dashboard | O09 | Required | Non-sensitive
withdrawal_followup_consent | Consent status for voluntary follow-up after interruption or withdrawal | categorical | yes; no; withdrawn; not approached | After interruption/withdrawal | Consent store | O05,O26 | Required before research follow-up | Highly confidential
interviewer_independent | Interviewer independent of supervision, assessment and progression decision | boolean | yes; no | Each qualitative encounter | Interview administration record | O06-O08,O24,O28 | Required | Confidential
cost_price_year | Costing base price year | integer | 2026 unless amended prospectively | Monthly/analysis | Cost assumptions | O25 | Required | Financial
cpi_adjustment_factor | Official consumer price index adjustment factor | number | 0+ | Monthly/analysis | Official CPI source | O25 | Missing only when no adjustment applies | Financial
exchange_rate_usd | Official Sierra Leonean leone to United States dollar exchange rate | number | 0+ | Costing period | Official exchange-rate source | O25 | Required for USD conversion | Financial
in_kind_valuation_method | Valuation method for donated labour or other in-kind resources | categorical/text | opportunity cost; replacement cost; other documented method | Monthly | I15/cost assumptions | O25 | Required for in-kind resources | Financial
overhead_allocation_method | Method used to allocate common overhead | categorical/text | recorded staff time; documented resource use; other prespecified rule | Monthly/analysis | I15/cost assumptions | O25 | Required when overhead is allocated | Financial
capital_useful_life_years | Useful life used for capital annualization | number | 3 for computers; 5 for other durable equipment; sensitivity range recorded | Analysis | Cost assumptions | O25 | Required for capital item | Financial
discount_rate | Annual discount rate used when timing spans more than one year | number | 0.03 base case; sensitivity values recorded | Analysis | Cost assumptions | O25 | Required when discounting applies | Financial
fidelity_due_status | Whether component is due in the measurement period | categorical | due; not due | Quarterly | I07 | O03 | Required | Sensitive
fidelity_applicable | Whether component applies to the programme/timepoint | categorical | yes; no | Quarterly | I07 | O03 | Required | Sensitive
fidelity_level_unit | Programme, site, resident, actor, product or control-cycle unit | text | Prespecified unit in Fidelity sheet | Quarterly | I07 | O03 | Required | Sensitive
fidelity_numerator | Observed count meeting component-specific evidence condition | integer/number | 0+; may be not applicable | Quarterly | I07 | O03 | Required when quantitative | Sensitive
fidelity_denominator | Count due or eligible under component-specific rule | integer/number | 0+; may be not applicable | Quarterly | I07 | O03 | Required when quantitative | Sensitive
fidelity_reviewer1_status | Primary IRET reviewer classification | categorical | met; partial; not met; unknown; not due; not applicable; disputed | Quarterly | I07 | O03 | Required | Confidential
fidelity_reviewer2_status | Independent IRET verifier classification | categorical | met; partial; not met; unknown; not due; not applicable; disputed | Quarterly | I07 | O03 | Required | Confidential
fidelity_adjudicated_status | Final IRET classification after reconciliation/adjudication | categorical | met; partial; not met; unknown; not due; not applicable; disputed | Quarterly | I07 | O03 | Required | Sensitive
fidelity_evidence_ids | Registered source-evidence identifiers supporting classification | text | One or more evidence IDs | Quarterly | I07 source register | O03 | Required | Confidential
fidelity_primary_source_type | Highest-tier primary evidence used | categorical | signed official record; secure system extract; official decision; register/log; portfolio/rubric record; financial record; other approved source | Quarterly | I07 | O03 | Required | Sensitive
fidelity_corroborating_source | Additional evidence used to verify or explain the component | text | Evidence ID or approved source description | Quarterly | I07 | O03 | Missing allowed when unavailable | Confidential
fidelity_discrepancy | Difference between reviewers or conflict in source evidence | text | None or documented discrepancy | Quarterly | I07 adjudication log | O03 | Required when disagreement exists | Confidential
fidelity_programme_response | Programme factual correction or clarification during query window | text | Response, evidence ID and date | Quarterly | I07 factual-query log | O03 | Missing if no query | Confidential
fidelity_adjudicator_id | Coded independent third adjudicator | text | IRET role code | Quarterly | I07 adjudication log | O03 | Required for unresolved disagreement | Confidential
fidelity_lock_version | Version of signed read-only fidelity dataset | text | Q#/M24-v# | Quarterly/M24 | IRET data-lock certificate | O03 | Required | Confidential
fidelity_lock_date | Date IRET research lead signs the fidelity data lock | date | YYYY-MM-DD | Quarterly/M24 | IRET data-lock certificate | O03 | Required | Sensitive
fidelity_iret_signoff | Named/coded IRET signatory and decision status | text/categorical | pending; signed plus coded signatory | Quarterly/M24 | IRET data-lock certificate | O03 | Required | Confidential
analysis_dataset_version | Version of locked analysis dataset used for each output | text | Analysis-v# | Each analysis/output | Analysis repository | O01-O28 | Required | Confidential
analysis_decision_log_id | Reference to prespecified or post-lock analytic decision record | text | ADL001+ | Each analysis | Analysis decision log | O01-O28 | Missing if none | Confidential
dissemination_output_id | Unique code for report, brief, article, presentation or repository output | text | DS001+ | At output | Dissemination register | O18-O20,O23-O28 | Required | Non-sensitive
dissemination_review_status | Status of factual/confidentiality/legal review | categorical | not due; under review; completed; released with unresolved disagreement | At output | Dissemination review log | O18-O20,O23-O28 | Required | Sensitive
dissemination_release_date | Date the IRET authorizes external release | date | YYYY-MM-DD | At output | Dissemination register | O18-O20,O23-O28 | Required for released outputs | Non-sensitive

## Fidelity_Tracker
Quarter | Component ID | Class | Due status | Applicable | Level/unit | Numerator | Denominator | Percent | Reviewer 1 status | Reviewer 2 status | Adjudicated status | Evidence IDs | Primary source type | Corroborating source | Data-quality issue | Adaptation ID | Corrective action | Programme factual response | Owner | Due date | Lock date | IRET sign-off
Prelaunch | F01 | Critical |  | Yes | Required governance bodies due
Prelaunch | F02 | Critical |  | Yes | Research authorization requirements
Prelaunch | F03 | Critical |  | Yes | Programme level
Prelaunch | F04 | Critical |  | Yes | Eight field sites
Prelaunch | F05 | Core |  | Yes | Residents and host institutions
Prelaunch | F06 | Core |  | Yes | Assigned programme actors
Prelaunch | F07 | Core |  | Yes | 17 modules
Prelaunch | F08 | Core |  | Yes | 70 planned sessions due
Prelaunch | F09 | Core |  | Yes | 36 practical exercises due
Prelaunch | F10 | Critical |  | Yes | Active resident-placement months
Prelaunch | F11 | Critical |  | Yes | Active residents
Prelaunch | F12 | Core |  | Yes | Planned mentor contacts and reviews
Prelaunch | F13 | Core |  | Yes | Formal reviews due
Prelaunch | F14 | Critical |  | Yes | Products due for assessment
Prelaunch | F15 | Critical |  | Yes | 15 residents
Prelaunch | F16 | Core |  | Yes | Active residents at M12
Prelaunch | F17 | Core |  | Yes | Active residents during M13-23
Prelaunch | F18 | Core |  | Yes | Active residents
Prelaunch | F19 | Core |  | Yes | High-stakes assessors and products
Prelaunch | F20 | Core |  | Yes | Quarterly control cycles due
Q1 | F01 | Critical |  | Yes | Required governance bodies due
Q1 | F02 | Critical |  | Yes | Research authorization requirements
Q1 | F03 | Critical |  | Yes | Programme level
Q1 | F04 | Critical |  | Yes | Eight field sites
Q1 | F05 | Core |  | Yes | Residents and host institutions
Q1 | F06 | Core |  | Yes | Assigned programme actors
Q1 | F07 | Core |  | Yes | 17 modules
Q1 | F08 | Core |  | Yes | 70 planned sessions due
Q1 | F09 | Core |  | Yes | 36 practical exercises due
Q1 | F10 | Critical |  | Yes | Active resident-placement months
Q1 | F11 | Critical |  | Yes | Active residents
Q1 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q1 | F13 | Core |  | Yes | Formal reviews due
Q1 | F14 | Critical |  | Yes | Products due for assessment
Q1 | F15 | Critical |  | Yes | 15 residents
Q1 | F16 | Core |  | Yes | Active residents at M12
Q1 | F17 | Core |  | Yes | Active residents during M13-23
Q1 | F18 | Core |  | Yes | Active residents
Q1 | F19 | Core |  | Yes | High-stakes assessors and products
Q1 | F20 | Core |  | Yes | Quarterly control cycles due
Q2 | F01 | Critical |  | Yes | Required governance bodies due
Q2 | F02 | Critical |  | Yes | Research authorization requirements
Q2 | F03 | Critical |  | Yes | Programme level
Q2 | F04 | Critical |  | Yes | Eight field sites
Q2 | F05 | Core |  | Yes | Residents and host institutions
Q2 | F06 | Core |  | Yes | Assigned programme actors
Q2 | F07 | Core |  | Yes | 17 modules
Q2 | F08 | Core |  | Yes | 70 planned sessions due
Q2 | F09 | Core |  | Yes | 36 practical exercises due
Q2 | F10 | Critical |  | Yes | Active resident-placement months
Q2 | F11 | Critical |  | Yes | Active residents
Q2 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q2 | F13 | Core |  | Yes | Formal reviews due
Q2 | F14 | Critical |  | Yes | Products due for assessment
Q2 | F15 | Critical |  | Yes | 15 residents
Q2 | F16 | Core |  | Yes | Active residents at M12
Q2 | F17 | Core |  | Yes | Active residents during M13-23
Q2 | F18 | Core |  | Yes | Active residents
Q2 | F19 | Core |  | Yes | High-stakes assessors and products
Q2 | F20 | Core |  | Yes | Quarterly control cycles due
Q3 | F01 | Critical |  | Yes | Required governance bodies due
Q3 | F02 | Critical |  | Yes | Research authorization requirements
Q3 | F03 | Critical |  | Yes | Programme level
Q3 | F04 | Critical |  | Yes | Eight field sites
Q3 | F05 | Core |  | Yes | Residents and host institutions
Q3 | F06 | Core |  | Yes | Assigned programme actors
Q3 | F07 | Core |  | Yes | 17 modules
Q3 | F08 | Core |  | Yes | 70 planned sessions due
Q3 | F09 | Core |  | Yes | 36 practical exercises due
Q3 | F10 | Critical |  | Yes | Active resident-placement months
Q3 | F11 | Critical |  | Yes | Active residents
Q3 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q3 | F13 | Core |  | Yes | Formal reviews due
Q3 | F14 | Critical |  | Yes | Products due for assessment
Q3 | F15 | Critical |  | Yes | 15 residents
Q3 | F16 | Core |  | Yes | Active residents at M12
Q3 | F17 | Core |  | Yes | Active residents during M13-23
Q3 | F18 | Core |  | Yes | Active residents
Q3 | F19 | Core |  | Yes | High-stakes assessors and products
Q3 | F20 | Core |  | Yes | Quarterly control cycles due
Q4 | F01 | Critical |  | Yes | Required governance bodies due
Q4 | F02 | Critical |  | Yes | Research authorization requirements
Q4 | F03 | Critical |  | Yes | Programme level
Q4 | F04 | Critical |  | Yes | Eight field sites
Q4 | F05 | Core |  | Yes | Residents and host institutions
Q4 | F06 | Core |  | Yes | Assigned programme actors
Q4 | F07 | Core |  | Yes | 17 modules
Q4 | F08 | Core |  | Yes | 70 planned sessions due
Q4 | F09 | Core |  | Yes | 36 practical exercises due
Q4 | F10 | Critical |  | Yes | Active resident-placement months
Q4 | F11 | Critical |  | Yes | Active residents
Q4 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q4 | F13 | Core |  | Yes | Formal reviews due
Q4 | F14 | Critical |  | Yes | Products due for assessment
Q4 | F15 | Critical |  | Yes | 15 residents
Q4 | F16 | Core |  | Yes | Active residents at M12
Q4 | F17 | Core |  | Yes | Active residents during M13-23
Q4 | F18 | Core |  | Yes | Active residents
Q4 | F19 | Core |  | Yes | High-stakes assessors and products
Q4 | F20 | Core |  | Yes | Quarterly control cycles due
Q5 | F01 | Critical |  | Yes | Required governance bodies due
Q5 | F02 | Critical |  | Yes | Research authorization requirements
Q5 | F03 | Critical |  | Yes | Programme level
Q5 | F04 | Critical |  | Yes | Eight field sites
Q5 | F05 | Core |  | Yes | Residents and host institutions
Q5 | F06 | Core |  | Yes | Assigned programme actors
Q5 | F07 | Core |  | Yes | 17 modules
Q5 | F08 | Core |  | Yes | 70 planned sessions due
Q5 | F09 | Core |  | Yes | 36 practical exercises due
Q5 | F10 | Critical |  | Yes | Active resident-placement months
Q5 | F11 | Critical |  | Yes | Active residents
Q5 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q5 | F13 | Core |  | Yes | Formal reviews due
Q5 | F14 | Critical |  | Yes | Products due for assessment
Q5 | F15 | Critical |  | Yes | 15 residents
Q5 | F16 | Core |  | Yes | Active residents at M12
Q5 | F17 | Core |  | Yes | Active residents during M13-23
Q5 | F18 | Core |  | Yes | Active residents
Q5 | F19 | Core |  | Yes | High-stakes assessors and products
Q5 | F20 | Core |  | Yes | Quarterly control cycles due
Q6 | F01 | Critical |  | Yes | Required governance bodies due
Q6 | F02 | Critical |  | Yes | Research authorization requirements
Q6 | F03 | Critical |  | Yes | Programme level
Q6 | F04 | Critical |  | Yes | Eight field sites
Q6 | F05 | Core |  | Yes | Residents and host institutions
Q6 | F06 | Core |  | Yes | Assigned programme actors
Q6 | F07 | Core |  | Yes | 17 modules
Q6 | F08 | Core |  | Yes | 70 planned sessions due
Q6 | F09 | Core |  | Yes | 36 practical exercises due
Q6 | F10 | Critical |  | Yes | Active resident-placement months
Q6 | F11 | Critical |  | Yes | Active residents
Q6 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q6 | F13 | Core |  | Yes | Formal reviews due
Q6 | F14 | Critical |  | Yes | Products due for assessment
Q6 | F15 | Critical |  | Yes | 15 residents
Q6 | F16 | Core |  | Yes | Active residents at M12
Q6 | F17 | Core |  | Yes | Active residents during M13-23
Q6 | F18 | Core |  | Yes | Active residents
Q6 | F19 | Core |  | Yes | High-stakes assessors and products
Q6 | F20 | Core |  | Yes | Quarterly control cycles due
Q7 | F01 | Critical |  | Yes | Required governance bodies due
Q7 | F02 | Critical |  | Yes | Research authorization requirements
Q7 | F03 | Critical |  | Yes | Programme level
Q7 | F04 | Critical |  | Yes | Eight field sites
Q7 | F05 | Core |  | Yes | Residents and host institutions
Q7 | F06 | Core |  | Yes | Assigned programme actors
Q7 | F07 | Core |  | Yes | 17 modules
Q7 | F08 | Core |  | Yes | 70 planned sessions due
Q7 | F09 | Core |  | Yes | 36 practical exercises due
Q7 | F10 | Critical |  | Yes | Active resident-placement months
Q7 | F11 | Critical |  | Yes | Active residents
Q7 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q7 | F13 | Core |  | Yes | Formal reviews due
Q7 | F14 | Critical |  | Yes | Products due for assessment
Q7 | F15 | Critical |  | Yes | 15 residents
Q7 | F16 | Core |  | Yes | Active residents at M12
Q7 | F17 | Core |  | Yes | Active residents during M13-23
Q7 | F18 | Core |  | Yes | Active residents
Q7 | F19 | Core |  | Yes | High-stakes assessors and products
Q7 | F20 | Core |  | Yes | Quarterly control cycles due
Q8 | F01 | Critical |  | Yes | Required governance bodies due
Q8 | F02 | Critical |  | Yes | Research authorization requirements
Q8 | F03 | Critical |  | Yes | Programme level
Q8 | F04 | Critical |  | Yes | Eight field sites
Q8 | F05 | Core |  | Yes | Residents and host institutions
Q8 | F06 | Core |  | Yes | Assigned programme actors
Q8 | F07 | Core |  | Yes | 17 modules
Q8 | F08 | Core |  | Yes | 70 planned sessions due
Q8 | F09 | Core |  | Yes | 36 practical exercises due
Q8 | F10 | Critical |  | Yes | Active resident-placement months
Q8 | F11 | Critical |  | Yes | Active residents
Q8 | F12 | Core |  | Yes | Planned mentor contacts and reviews
Q8 | F13 | Core |  | Yes | Formal reviews due
Q8 | F14 | Critical |  | Yes | Products due for assessment
Q8 | F15 | Critical |  | Yes | 15 residents
Q8 | F16 | Core |  | Yes | Active residents at M12
Q8 | F17 | Core |  | Yes | Active residents during M13-23
Q8 | F18 | Core |  | Yes | Active residents
Q8 | F19 | Core |  | Yes | High-stakes assessors and products
Q8 | F20 | Core |  | Yes | Quarterly control cycles due
M30 | F01 | Critical |  | Yes | Required governance bodies due
M30 | F02 | Critical |  | Yes | Research authorization requirements
M30 | F03 | Critical |  | Yes | Programme level
M30 | F04 | Critical |  | Yes | Eight field sites
M30 | F05 | Core |  | Yes | Residents and host institutions
M30 | F06 | Core |  | Yes | Assigned programme actors
M30 | F07 | Core |  | Yes | 17 modules
M30 | F08 | Core |  | Yes | 70 planned sessions due
M30 | F09 | Core |  | Yes | 36 practical exercises due
M30 | F10 | Critical |  | Yes | Active resident-placement months
M30 | F11 | Critical |  | Yes | Active residents
M30 | F12 | Core |  | Yes | Planned mentor contacts and reviews
M30 | F13 | Core |  | Yes | Formal reviews due
M30 | F14 | Critical |  | Yes | Products due for assessment
M30 | F15 | Critical |  | Yes | 15 residents
M30 | F16 | Core |  | Yes | Active residents at M12
M30 | F17 | Core |  | Yes | Active residents during M13-23
M30 | F18 | Core |  | Yes | Active residents
M30 | F19 | Core |  | Yes | High-stakes assessors and products
M30 | F20 | Core |  | Yes | Quarterly control cycles due

## Cost_Assumptions
Supplementary File 6: Economic costing assumptions
Protocol Version 1.2 ¦ 17 August 2026 ¦ Assumptions are prespecified and reported with source/date in the empirical paper.
Assumption | Base specification | Reporting rule | Sensitivity analysis
Perspective | Provider perspective | Separate programme delivery, implementation strategies and research-only evaluation costs. | Report alternative decision-maker totals where useful.
Price year and currency | Constant 2026 Sierra Leonean leones; convert to USD with mean official exchange rate for the costing period. | Report exchange-rate source and date range. | Vary exchange-rate date window when volatility could affect interpretation.
Inflation adjustment | Adjust expenditure from another year with the official consumer price index. | Report index source, base and calculation. | Use plausible alternative CPI values when source uncertainty exists.
Labour valuation | Loaded salary plus approved benefits. | Record actor, time, preparation, travel and delivery separately. | Vary staff time and loaded rates.
Donated and in-kind resources | Opportunity-cost valuation; replacement cost may support sensitivity analysis when opportunity cost is not observable. | Record valuation source and payer/owner. | Vary in-kind value and exclude it in a financial-expenditure scenario.
Overhead allocation | Allocate common overhead by recorded staff time or documented resource use. | State allocation base for every shared cost pool. | Compare time-based, use-based and excluded-overhead scenarios.
Capital useful life | Three years for computers; five years for other durable equipment. | Use straight-line annualization and documented programme-use share. | Vary useful life by ±2 years where plausible.
Discounting | 3% annual rate when cost timing spans more than one year. | State timing convention and whether discounting applies. | Repeat at 0% and 5%.
Cohort scale | Base cohort: 15 residents across eight sites. | Separate fixed and variable cost components. | Model smaller and larger cohorts without assuming linear scale economies.
Travel and field intensity | Observed monthly travel, deployment and field-resource use. | Use event-specific microcosting for authentic investigations. | Vary travel intensity and emergency-deployment costs.

## Continuity
Supplementary File 6: Operational continuity and contingency controls
Controls protect core functions, safety and fairness during prolonged programme delivery. Every activation enters the continuity and adaptation record.
Risk or disruption | Trigger/example | Prespecified control | Documentation and decision
Mentor loss or overload | Departure, conflict, prolonged absence or caseload above four residents | Substitute mentor pool, specialist backup, temporary redistribution and protected transition briefing | Conflict declaration; replacement decision; missed-contact recovery plan; quarterly review
Resident interruption | Illness, family responsibility, deployment, safety or other approved interruption | Temporary interruption, protected return plan and completion window not exceeding three months unless amended | Cohort flow; reason; consent status; progression committee decision; appeal route
Field-site loss or suspension | Safety failure, data-access loss, supervision failure or site withdrawal | Suspend placement, protect records and reassign to an accredited alternative site | Incident/site decision; adaptation log; new learning agreement; ethics review when risk or data route changes
Insufficient authentic investigation opportunity | National incidence does not provide two qualifying opportunities per resident | Regional deployment, urgent cluster investigation, vaccine-safety event, environmental/occupational event, humanitarian assessment or other authentic event with a real decision pathway | Opportunity log; role assignment; programme-led corrective placement; FP2 verification
Power, internet or platform failure | Connectivity interruption, device failure or inaccessible platform | Printed/offline materials, approved offline capture, power backup and deferred secure synchronization | Failure log; alternative used; data-security check; restored-service verification
Public health emergency or political/security disruption | Emergency redeployment, unsafe movement, unrest or restricted operations | Immediate safety action, emergency communication, remote/offline delivery, safe pause or site reassignment | Risk assessment; authority notification; adaptation or amendment; continuation decision
Financing interruption | Loss or delay of core programme or evaluation funds | Contingency reserve, escalation to steering committee, protection of safety/supervision and staged pause when critical gates fail | Cost/risk dashboard; corrective plan; stop/continue decision; sustainability review
Data, laboratory or specialist-access loss | Permission change, system outage, specimen/laboratory interruption or specialist unavailability | Alternative approved data route, specialist network, revised sequence or safe substitute field assignment preserving core function | Data-governance review; adaptation log; revised milestone and verification

## Revision_Log
Supplementary File 6: Version and revision record
Version | Date | Scope | Status or required action
0.1 | 21 July 2026 | Initial prospective protocol workbook for ethics, registration and journal review. | Source package records no recruitment or research data collection.
0.2 | 17 August 2026 | Reviewer-responsive outcome hierarchy, threshold rationale, fidelity scoring, assessment and interviewer preparation, costing assumptions, continuity controls and new variables. | Corresponding author must reconfirm current study status, author approval, references and journal limits before upload.
0.3 | 17 August 2026 | Independent Research and Evaluation Team governance; operational fidelity definition; component-level numerator, denominator, source and verification matrix; expanded I07 tracker; complete analysis matrix; dissemination plan and release controls. | No recruitment or research data collection in the source record; corresponding author must reconfirm current study status and approve IRET terms before upload.
1 | 17 August 2026 | Final coordinated audit: key-secondary hierarchy; separation of field-practice delivery from attainment; two-figure manuscript; complete Supplements 1-9; no-CI component census; independent scoring, analysis and dissemination controls. | No recruitment or research data collection in the source record; corresponding author must reconfirm current status, author approval and final source verification before upload.

## Independent_Team
Role | Minimum competencies | Independence requirement | Core responsibilities | Restricted activities | Data access | Decision/output authority | Backup/conflict control
IRET research lead | Implementation research; mixed methods; research ethics; protocol governance; scientific reporting | No programme management, teaching, mentorship, supervision, assessment, examination or progression role | Leads research governance, protocol adherence, interpretation, reports, publications and external communication | Cannot direct resident progression, change programme records or overrule safeguarding action | Approved research extracts, locked analysis data and aggregate safety information | Signs analysis plans and data locks; approves research outputs and unresolved analytic decisions | Deputy research lead named; annual and event-triggered conflict review
Fidelity and quantitative analyst | Implementation fidelity; data management; descriptive and longitudinal statistics; reproducible coding | No responsibility for delivering or assessing any scored programme component | Registers source evidence, conducts Reviewer 1/Reviewer 2 scoring, supports adjudication, analyzes O01-O24 and O26-O28 | Cannot create source records, choose programme corrective actions or score resident competence | Registered source-evidence package and coded quantitative datasets | Prepares component matrices, fidelity scores, statistical tables and sensitivity analyses | Second analyst or external methodologist available for adjudication and code review
Qualitative lead | Qualitative design; Framework Method; reflexivity; power-sensitive interviewing; disclosure control | No supervisory, assessment, examination, grievance-decision or progression relationship with participants | Leads sampling, interviewer preparation, codebook, matrix analysis, negative-case review and integration | Cannot disclose identifiable responses to programme or assessment personnel | De-identified transcripts, field notes and qualitative matrices | Approves qualitative findings, quotation use and contribution to joint displays | Independent senior qualitative reviewer available for difficult disclosure or interpretation decisions
Independent interviewers | Ethics; informed consent; qualitative interviewing; distress response; confidentiality; field-note preparation | No direct reporting, mentorship, assessment or employment-management relationship with invitees | Obtain consent; conduct interviews/focus groups; prepare field notes and reflexive records | Cannot collect academic evidence or report individual opinions to programme supervisors | Only assigned participant contact details and secure recording/transcription system | Record data but do not make programme decisions | Interviewer substitutions recorded; relationship and conflict declarations completed before each wave
IRET data manager | Secure database design; access control; de-identification; audit trails; version control; disclosure review | No assessment or progression role and no sole authority to interpret outcomes | Maintains consent linkage, source-evidence register, validation rules, query log, read-only locks and repository package | Cannot release identifiable data or change locked values without a versioned correction | Identifiable linkage store and all approved research databases under least-privilege controls | Issues validation reports, lock certificates, correction logs and disclosure clearance | Named deputy; quarterly access review; recovery and business-continuity testing
IRET health economist | Health/programme costing; time-driven activity-based costing; inflation, currency and sensitivity analysis | No authority over programme procurement, payments or resident support decisions | Values programme, implementation-strategy and research-only resources; prepares cost and unit-cost analyses | Cannot approve expenditure or alter source financial records | Approved financial extracts, time logs and cost assumptions; no unnecessary personal identifiers | Signs cost-methods record and economic outputs | Independent verification of unit costs, exchange rates, inflation factors and allocation assumptions
Third adjudicator/quality reviewer | Senior implementation science or evaluation expertise; no connection to the disputed component | Independent of both initial reviewers and the programme unit whose evidence is disputed | Adjudicates unresolved fidelity classifications; reviews major analytic disagreements and code quality | Cannot adjudicate a component where a personal, institutional or financial conflict exists | Bounded source package and reviewer rationales needed for the decision | Records final status, rationale, evidence basis and minority view | Alternative adjudicator roster maintained; every recusal recorded

## Analysis_Plan
Domain/outcome | Primary estimand or analytic question | Population/denominator | Source and lock | Primary analysis | Missing/unknown rule | Sensitivity/fallback | Planned output | IRET lead
O03 Overall fidelity | Exact percentage of due and applicable components independently adjudicated as met at each quarter and Month 24; status of every critical component | Complete prespecified set of 20 components; denominator excludes not-due and IRET-approved not-applicable items | I07 source-evidence register, two independent reviews, adjudication file and signed quarterly/Month-24 lock | Component matrix; 100 x met/due-applicable; no sampling confidence interval for the 20-component census; exact critical-component table | Partial, not met, unknown and unresolved disagreement = failure; not-due excluded; not-applicable requires written rationale | Unknown/disputed failed versus excluded; strict Month 24 versus approved window; original form versus fidelity-preserving adaptation; all evidence versus highest-tier evidence | Quarterly heatmap; Month-24 primary fidelity table; critical-component table; progression classification | Fidelity/quantitative analyst
O01-O02 Reach and adoption | Proportion of eligible applicants offered/enrolled; proportion of invited eligible sites accredited and active | Applicants/eligible offers; invited eligible sites | Recruitment and site registers after IRET validation | Counts, exact denominators, Wilson 95% confidence intervals and reasons for non-enrolment/non-adoption | Unknown eligibility or invitation status shown separately | Alternative eligibility definitions and late site activation | Cohort/site flow table | Quantitative analyst
O04 Field-practice attainment | Proportion of enrolled residents completing at least 68 verified qualifying weeks by Month 24 or approved completion window | Enrolled cohort; active cohort also shown descriptively | Verified field-week, placement and deployment logs after IRET source checks | Count, proportion, Wilson 95% confidence interval, distribution of weeks and reasons for shortfall | Missing documentation remains unknown until IRET distinguishes activity failure from documentation failure | Strict Month 24 versus approved three-month window; interruption-inclusive versus calendar-time display | Field-week accumulation figure and attainment table | Quantitative analyst
O05 Retention | Proportion of enrolled residents active at Months 12 and 24; timing and reasons for interruption or withdrawal | Enrolled cohort | Cohort register and documented status after lock | Count, proportion, Wilson interval, cohort-flow diagram and descriptive time-to-status | Temporary interruption retained; permanent withdrawal not recoded as missing | Active-status definitions and approved return windows | Cohort flow and retention table | Quantitative analyst
O06-O08 AIM/IAM/FIM | Stakeholder-group means, distributions and changes in acceptability, appropriateness and feasibility | Research-consenting residents, mentors, supervisors and faculty by wave | I03 survey dataset after item-level validation and lock | Item distributions; scale mean/SD and 95% CI when at least 3/4 items answered; stakeholder/wave displays; internal consistency when estimable | No scale score when fewer than three items answered; nonresponse reported by role/wave | Complete cases; medians when skewed; exploratory repeated model only when cell size and convergence permit | Role-by-wave table and integrated figure | Quantitative analyst
O09-O12 Data and delivery processes | Completeness, instructional dose, mentorship dose and progression-review timeliness | Required fields, sessions/exercises due, mentor contacts due and progression reviews due | Data-quality dashboard and programme records after quarterly lock | Numerators, denominators, percentages, trends and component-level linkage to fidelity | Unknown and late records shown; no imputation to improve apparent delivery | Strict schedule versus approved operational window | Quarterly process dashboard | Fidelity/quantitative analyst
O13-O15 Portfolio and outbreak evidence | Completion and quality of field products; authentic investigation opportunities and analytic leadership | Enrolled and active cohorts; products/opportunities due | Portfolio, rubric, role statement and outbreak evidence maps after source verification | Completion proportions, rubric distributions, timeliness, opportunity versus resident-performance failure and site opportunity display | Missing source evidence remains unknown until verification | Approved completion window; high-stakes product evidence tiers | Portfolio/outbreak table and opportunity matrix | Quantitative analyst
O16-O20 Research, thesis and dissemination milestones | Completion and timing of 13 milestones; thesis approval; internal publications; peer-reviewed manuscript; policy/scientific dissemination | Enrolled cohort, with active-cohort opportunity descriptions | I09 milestone, examination, editorial and event records after lock | Milestone proportion, cumulative incidence description, actual month, delay reasons and output status through Month 30 | External editorial delay shown separately from resident or programme delay | On-time versus approved recovery; submitted versus accepted/published status | Milestone figure and output-status table | Quantitative analyst
O21 Competency change | Observed change in applied reasoning and workplace entrustment evidence from baseline to Months 12 and 24 | Residents with valid paired measures; full wave distributions also shown | Applied assessment and competency records after calibration and lock | Paired mean or median change; 10,000-resample resident bootstrap only when stable; descriptive distributions | Complete-pair analysis; reasons for missing assessment reported | Observed ranges when bootstrap unstable; exploratory linear/ordinal mixed model only when assumptions permit | Competency-change figure and validity-evidence table | Quantitative analyst
O22 Assessor agreement | Agreement on critical decisions and composite scores for double-rated products | All theses/dissertations and at least 25% of other high-stakes products | Paired rubrics, calibration and disagreement logs | Confusion matrix and exact agreement; weighted kappa and two-way random-effects absolute-agreement ICC only when variation and sample support estimation | Unscored or recused ratings documented; no invented paired values | Score-difference distribution and qualitative disagreement review when coefficients are unstable | Agreement table and assessment-validity evidence | Quantitative analyst
O23-O24 Uptake and system contribution | Recommendation status and independently verified changes linked to resident work | Recommendations with named decision owner; verified contribution cases | I14 forms, documentary evidence and decision-user interviews after Month-24/30 lock | Status proportions, time to decision, contribution-strength rubric and cautious narratives with alternative explanations | Unverified claims remain unverified and do not count as completed contribution | Narrow versus inclusive contribution definition | Uptake table and contribution narratives | Mixed-methods lead
O25 Cost | Total and component cost and unit costs per enrollee, retained resident, graduate, product, investigation, publication and thesis | Provider-perspective programme, implementation-strategy and research-only resources | I15 time/cost logs, financial extracts and cost assumptions after economic lock | Time-driven activity-based costing; constant 2026 leones; official CPI and exchange rate; capital annualization; documented overhead allocation | Missing quantities/values flagged and valued only through prespecified transparent estimates | Staff time, in-kind valuation, overhead, useful life, discount rate, cohort size, travel and publication charges | Cost table, cost breakdown and unit-cost figure | Health economist
O26 Equity | Differences in opportunity and outcomes across ethics-approved equity strata | Approved strata with disclosure-safe cells | Linked programme and consenting survey data after disclosure review | Descriptive differences and confidence intervals where stable; exposure before outcome; qualitative explanation | Prefer-not-to-say retained; cells smaller than five suppressed | Defensible category combination; no unstable multivariable subgroup models | Equity table and joint display | Quantitative/qualitative leads
O27 Safety, safeguarding and integrity | Number, type, severity, response time, resolution and recurrence of events | All reported events and programme periods at risk | Restricted incident extract approved for research use | Aggregate counts, timelines, corrective-action status and case-free narrative when disclosure risk prevents detail | No imputation; confidential unknowns remain bounded and reported to oversight | Severity reclassification after independent review | Safety table and non-compensatory progression decision | Research lead with safeguarding lead
O28 Sustainability readiness | Readiness of financing, faculty, mentors, governance, sites, curriculum, data systems and graduate deployment | Programme and eight sites at Months 18, 24 and 30 | Scorecard, documents and interviews after lock | Domain status, evidence matrix and qualitative explanation; no unsupported composite claim | Unknown readiness domains remain unknown | Strict evidence tier and recoverability scenarios | Sustainability scorecard and scale-up implications | Mixed-methods lead
Qualitative process evaluation | How context, mechanisms, workload, opportunity, adaptation, equity, safety and sustainability explain implementation | Maximum-variation sample with longitudinal reinterviews until information power is sufficient | De-identified recordings/transcripts, field notes, reflexive memos and versioned framework matrices | Framework Method; CFIR and implementation-outcome matrix plus open coding; at least 20% independently coded; negative cases and longitudinal comparison | No forced saturation claim; withheld or unsafe quotations omitted; reasons for nonparticipation reported where known | Alternative codebook interpretations, bounded stakeholder interpretation and independent analytic review | Themes, supported quotations, role/site/time comparison and explanatory matrices | Qualitative lead
Mixed-methods integration | How quantitative outcomes, fidelity, qualitative explanations, adaptations, cost, equity and context combine to support the scale-up decision | All locked quantitative, qualitative and economic results | Versioned joint-display dataset and interpretation log | Joint displays classify convergence, complementarity, dissonance or silence; dissonance triggers source review or bounded additional analysis | Missing strand remains visible rather than replaced | Alternative weighting of evidence and minority interpretation recorded | Integrated conclusions and green/amber/red decision record | Research lead

## Dissemination
Audience | Output | Core content | Timing | IRET lead | Review/decision boundary | Delivery channel | Required record/indicator
Residents and programme actors | Plain-language quarterly dashboard; Month-24 findings meeting; Month-30 summary | Fidelity status, delivery progress, data quality, workload, safety, adaptations, corrective actions and uncertainties without disclosing voluntary individual responses | Quarterly; M24; M30 | Research lead with fidelity analyst | Programme response appears separately. No confidential survey/interview response enters progression or supervision. | Secure dashboard, facilitated interpretation meeting and written summary | Dashboard version; attendance; questions; response and closed-action log
Field sites and decision users | Site-confidential fidelity and opportunity report; product follow-up; contribution verification | Site-specific source-supported delivery, field opportunity, mentorship, data quality, adaptations, resident product use and corrective actions | Quarterly; M24; M30 | Fidelity analyst and mixed-methods lead | Site may correct facts and propose action during the five-working-day fidelity query and 15-working-day report review. IRET retains scoring and interpretation. | Confidential site report and review meeting | Factual-query log; site response; action owner, due date and verification
NPHA, steering and national governance | Month-12 interim report; Month-24 final implementation, cost, equity, safety and scale-up report; Month-30 follow-up | Primary fidelity result; every critical component; feasibility, educational, service, economic, equity, safety and sustainability findings; green/amber/red classification and corrective-action feasibility | M12; M24; M30 | IRET research lead | NPHA records management response and scale-up decision. It cannot revise locked analysis, remove unfavorable findings or require a green conclusion. | Signed technical report, governance presentation and decision meeting | Signed report; minutes; management response; minority view and decision record
SLESRC and independent oversight | Progress, deviation, amendment, safety, privacy, integrity and close-out reports | Required ethics information, serious events, corrective actions, protocol amendments, data breaches and study closure | Under approval conditions; immediately for reportable events; close-out | IRET research lead and safeguarding lead | Reporting follows ethics conditions, law and institutional policy. Urgent protective action is not delayed for routine review. | Formal submission through approved channels | Submission date; acknowledgement; ethics decision; action closure
National partners and policy users | Policy brief, technical workshop and decision slide deck | What worked, what failed, cost, equity, system contribution, sustainability requirements and concrete refinements for later cohorts or scale-up | After M24; update at M30 | IRET with NPHA dissemination focal point | Factual, confidentiality and disclosure review only. Findings, uncertainty and adverse results remain intact. | Policy brief, stakeholder workshop and technical presentation | Final brief; workshop report; participant list; feedback and action commitments
Scientific community | Registered protocol; primary empirical mixed-methods article; distinct cost or assessment paper when justified; conference outputs | Prespecified methods, fidelity, implementation, education, service contribution, cost, equity, safety, limitations and scale-up decision | Protocol before enrolment; primary results after M30 or earlier only when prespecified and analytically complete | IRET and contribution-based author group | Authors and institutions receive 15 working days for factual accuracy, confidentiality, legal and third-party rights review. No institutional publication veto. | Peer-reviewed journal, conference oral/poster presentation and methods repository | Submission and peer-review records; reporting checklist; presentation evidence; authorship record
Public and repository users | Plain-language public summary; permitted protocol materials, instruments, metadata, code and aggregate or de-identified outputs | Study purpose, methods, principal findings, limitations, safeguards, decisions and reusable non-confidential resources | After disclosure, ethics and rights review | IRET data manager and research lead | Release follows ethics, confidentiality, law and third-party rights. Direct identifiers and unsafe small-cell or deductively identifying information are excluded. | Stable public repository and approved public communication channels | Repository DOI/version; disclosure checklist; data/code licence and access statement
Dissemination principles and release controls
Fixed review period | 15 working days for factual accuracy, confidentiality, legal restrictions and third-party rights unless urgent safety reporting applies.
No veto | Programme or institutional reviewers cannot alter locked analyses, remove unfavorable findings, block publication or require a preferred progression classification.
Negative results | Red, amber, null, harmful and unfavorable findings receive the same reporting commitment as favorable findings.
Audit trail | IRET records every draft version, reviewer comment, response, unresolved disagreement, disclosure decision, submission and publication status.